## RESULTS
MBSE Canberra Symposium 2014, Workshop, The challenges of depoying MBSE solutions
Legend: TQIS = Thales Quick Internal Survey MCW = MBSE Canberra Workshop Participants: 35 MBSE Symposium participants 20 Thales participants Coordinators: Stéphane Bonnet (Thales Corporate Engineering) Fabrice Lestideau (Thales Australia)
Enabler / Obstacle | Classification | Source | Factor
Enabler | Coaching | TQIS, MCW | Beyond initial training, continued mentoring and coaching helps MBSE claimed benefits to be effectively realised and implementation to persist
Enabler | Coaching | TQIS, MCW | Presence of LOCAL modelling champions within project teams, with proximity support and coaching on all aspects (process, methods, and tools)
Enabler | Coaching | MCW | Training and coaching adapted to the user objectives, related to the job they are doing
Obstacle | Coaching | MCW | Having the wrong MBSE champion. People attack the person, not the initiative
Enabler | Commitment to MBSE | TQIS, MCW | Corporate commitment: If MBSE is part of performance plans, acceptance by local management is easier.
Enabler | Commitment to MBSE | MCW | Convinced senior managers / decision makers
Enabler | Commitment to MBSE | MCW | Individual commitment to train
Enabler | Commitment to MBSE | TQIS | Top management mandating MBSE on flagship projects
Enabler | Commitment to MBSE | TQIS | Committed and hard-working engineers (evangelists, local support, operational engineers)
Enabler | Commitment to MBSE | TQIS | Strong direction and commitment from Operational Managers
Obstacle | Commitment to MBSE | MCW | Lack of management commitment and funding
Obstacle | Commitment to MBSE | MCW | Stakeholders not engaged / commited
Obstacle | Commitment to MBSE | MCW | Change of strategy following a change of managment. It takes only one decision at management level to stop an initiative.
Obstacle | Commitment to MBSE | TQIS | Failure to recognise the needs of the Organisation outside of the project. Conflict between short term project needs and long term product/business needs). Need strong involvement of actors and management to understand the overall picture. 2 examples: - Time spent refining the need understanding is time that will be gained later on. But the workload association to specification phase effort is often suited - Generating artefacts has a cost. Project actors prefer immediate benefits even if they perceive the long-term added-value.
Obstacle | Commitment to MBSE | MCW | It only takes one decision from one manager at one level to kill an MBSE initiative (motivated by uncertainty, risk of changing from current practices)
Obstacle | Commitment to MBSE | TQIS | Lack of sponsoring from senior engineers or managers
Obstacle | Commitment to MBSE | TQIS | Bad understanding of the outcome of the model from the management / decision makers
Obstacle | Commitment to MBSE | TQIS | MBSE not being mandatory
Enabler | Cultural Change | TQIS | Having existing engineering practices already close to the promoted method even though not MBSE
Enabler | Cultural Change | TQIS | Modelling is more interesting and motivating than standard requirement engineering: It allows focusing on problems on a more technical maner (in comparison with the art of writing)
Obstacle | Cultural Change | TQIS, MCW | Natural resistance to change: Engineers (and managers) do not think they need MBSE (until they try it).
Obstacle | Cultural Change | TQIS, MCW | Underestimating the change: MBSE has a major impact on the daily activities of engineers. That can make them (and their managers) feel unsecure.
Obstacle | Cultural Change | TQIS | MBSE does not come alone: It implies changes in configuration management, requirements management and other disciplines. The impacts of MBSE cannot be confined to a sole engineering activity. Even generated documents are likely to be different and to unsettle the other stakeholders.
Obstacle | Cultural Change | MCW | It is difficult to get the model accepted as THE reference / master, in particular by configuration managers for who documents are the graal
Obstacle | Cultural Change | MCW | Accumulation of constraints: Culture, stil having Customer requirements, security management, change management, etc.
Obstacle | Cultural Change | TQIS | People are very used to Visio especially in the bid phases: Mentioning MBSE usually scares (perceived as too complex to manage for bid phase, outputs not as “nice” as Visio, etc.)
Obstacle | Cultural Change | TQIS | Shift of methodology is not yet sufficiently reflected in the current company processes and expected documents. MBSE should not be considered as a "nice to have" only.
Obstacle | Cultural Change | TQIS | MBSE implies reduced freedom for engineers (especially when modelling guidelines are set up). This reduction of freedom has to be compensated by an increase of work interest.
Obstacle | Cultural Change | TQIS | Not having the model at the center of the engineering activities. If not on the critical path or not considered as THE reference, the modelling activity will not be allocated the required resource
Obstacle | Cultural Change | TQIS | Lack of domain engineers commitment. The modelling team cannot be isolated.
Obstacle | Cultural Change | TQIS | Usage of models in parallel to classical requirements-based systems engineering (duplicate work)
Obstacle | Cultural Change | TQIS | Bad understanding of the value of a model at system level, which might be considered as too abstract & too vast, not addressing a specific problem or requiring too much much to achieve
Enabler | Deployment Strategy | MCW | Being modest in setting the first objectives, allowing for an incremental approach to deployment
Enabler | Deployment Strategy | MCW | Organization-wide deployment instead of project-specific deployment, having a structured implementation of MBSE
Enabler | Deployment Strategy | TQIS, MCW | Experimenting in good conditions on well-chosen pilot projects (topic, timing, objectives, etc.)
Enabler | Deployment Strategy | MCW | Being able to trial approaches, tools, methods
Enabler | Deployment Strategy | MCW | Incremental, bottom-up uptake based on benefit demonstration
Enabler | Deployment Strategy | TQIS | Foster an active MBSE / System Engineering community (shared return on experience, etc.)
Enabler | Deployment Strategy | MCW | Implication of (a large number of) sub-contractors: model sharing, model-based discussions, etc.
Enabler | Deployment Trick | TQIS | Creating pairs mixing 2 types of engineers: “domain” engineers and “MBSE” engineers. Both are going to learn from each other.
Enabler | Deployment Trick | TQIS | Get different teams onboard (for example co-engineering SE & SW, safety analysts, IVV practitioners)
Enabler | Expected Benefits | TQIS, MCW | The perspective to have a shared reference / understanding, easier communication and maintenance of engineering artefacts is a motivation to embrace MBSE.
Enabler | Expected Benefits | MCW | Once something is in the model, it becomes THE reference (even with an incremental rollout)
Enabler | Expected Benefits | MCW | Ability for MBSE to support other disciplines (RAMS, etc.)
Enabler | Expected Benefits | TQIS, MCW | Being able to generate artefacts (code, documents, configuration files) from models. The existence of models is less challenged when they are used to produce engineering artefacts
Enabler | Expected Benefits | TQIS | Being able to model / reverse engineer (or automatically recreate) an existing architecture / system, and build on top of this model
Enabler | Expected Benefits | TQIS | Being able to prove easier impact analysis with traceability beThales Internal Survey + MBSE Symposium Workshopeen requirements, models, interfaces and test procedures
Enabler | Expected Benefits | TQIS | Showing quick wins: initialisation of a model from existing Excel material, ability to quickly produce outputs, etc.
Enabler | IT Policies and Tool Support | TQIS | Having the ability to develop tools and add-ons (accelerators, checkers, import/export, model batch correction, etc.). This can help make the model the producer of outputs for other engineering activities.
Enabler | IT Policies and Tool Support | TQIS | Having the complete tool chain ready to generate artifacts before the operational project actually starts
Obstacle | IT Policies and Tool Support | MCW | Tool endorsement from IT or security. IT business rules can make the deployment of new tools complicated
Obstacle | IT Policies and Tool Support | MCW | Model security classification & ITAR (unclassified vs TSVP security clearance)
Obstacle | IT Policies and Tool Support | TQIS | Local support team not sized correctly and not able to quickly respond to operational needs
Obstacle | IT Policies and Tool Support | MCW | Access to modelling tools: Organizations making tool procurement difficult
Obstacle | IT Policies and Tool Support | TQIS | Infrastructure issues (installation, administration, configuration, mutli-site, VMs, etc.). Using a MBSE tool should be as simple as getting Visio installed and running.
Obstacle | Learning Curve | TQIS, MCW | Understanding how MBSE can be implemented, how to express design ideas with models takes time and require practice
Obstacle | Learning Curve | TQIS | Lack of modeling skills. Modeling requires a certain ability in abstract thinking and it might take time to acquire this ability.
Obstacle | Learning Curve | MCW | New initiatives reduce productivity of current workforce during startup
Enabler | MBSE Examples | MCW | (Bad) lessons learned from previous projects where MBSE was not applied
Enabler | MBSE Examples | TQIS | Being able to demonstrate benefits (success stories) on other (preferably significant) projects with different scopes and objectives
Enabler | MBSE Examples | TQIS | Previous experience with model-based approach within a team
Obstacle | MBSE Examples | MCW | Lack of success stories to rely on
Obstacle | MBSE Examples | TQIS | Misusage of the method (for example, elements of solution in problem description space) leading to bad results and experiences, likely to discourage other initiatives (in the same team or just beside)
Enabler | Modelling Guidelines | TQIS, MCW | Having (customized) guidelines, both at company and project levels, explaining which tool/method/practices to apply and how (definition of the modelling strategy).
Enabler | Modelling Guidelines | TQIS | Giving an easy access to modelling guidelines (shared wiki for example)
Obstacle | Modelling Guidelines | TQIS | Lack of methodology: Methodology help define modelling practices, objectives and give semantics to models
Obstacle | Modelling Guidelines | MCW | Lack of modelling guidelines: Method and tool appropriation is necessary
Obstacle | Modelling Guidelines | TQIS | Lack of common guidelines for different projects in the same structure
Enabler | Modelling Objectives | TQIS, MCW | Having a strong focus on the modelling goals and make sure that all activities around MBSE contribute to these goals. One should not sell the wrong thing (MBSE instead of its outcomes, modelling is not the goal.).
Obstacle | Modelling Objectives | TQIS, MCW | Not having clear objectives for the program: Who will benefit from MBSE, what will be the outputs of the model, etc.
Obstacle | Modelling Objectives | TQIS | Unclear (or conflictual) views of the objectives or the strategy to achieve them
Obstacle | Not MBSE-specific | TQIS | Users not thinking they have a problem to solve, being more project-oriented than not product-oriented
Obstacle | Not MBSE-specific | TQIS | Co-engineering between System Engineers and Sotware Engineers is difficult to implement
Enabler | Other Stakeholders | MCW | Customer commited to MBSE
Obstacle | Other Stakeholders | MCW | Customer mandating another process
Enabler | ROI Measurement | MCW | Being able to show metrics (cost, schedule, technical) for IVV in order to track MBSE efficiency
Obstacle | ROI Measurement | TQIS, MCW | Current inability to show / prove quantifiable ROI, especially given the required efforts: Learning, Training, Mentoring, Modelling. Case studies and figures are difficult to find.
Obstacle | ROI Measurement | MCW | Complexity of explaining the benefits / proving the ROI results in a lack of sponsorship / commitment
Obstacle | ROI Measurement | TQIS | Lack of metrics on design errors raised during integration, verification & validation phases to demonstrate MBSE benefits (and related costs). Comparing before / after usually requires metrics and protocoles that are stable in time.
Enabler | Sponsorship | MCW | Having management and leaders ready to fund the effort
Obstacle | Sponsorship | MCW | Lack of funding / resource. Licences, activity overhead, training, etc.
Obstacle | Sponsorship | MCW | Lack of funding for research, experimentation, tooling, training, etc.
Enabler | Tooling | TQIS, MCW | Modelling tools on the market are getting better: Enhanced features and user-friendliness are improving over time. They become on easier sell.
Enabler | Tooling | MCW | Modelling tools can easily integrate with other tools like PLM, CM, etc.
Enabler | Tooling | TQIS | Collaborative capability of the tool: Several engineers have to contribute to the model simultaneously and seamlessly
Obstacle | Tooling | MCW | Bad tool interoperability (lack of openness). There is a barrier is putting a lot of effort into modelling and being locked into a tool over time. Interoperability is also necessary between tools for specific analyses.
Obstacle | Tooling | TQIS, MCW | Steep learning curve
Obstacle | Tooling | MCW | Incompatibility between tool versions (older version of the modelling tool required -- for example to interoperate with other tools -- while newer version would be needed)
Obstacle | Tooling | MCW | Lack of perception of the value of the modelling tool seen as just another drawing tool.
Obstacle | Tooling | MCW | (Non) ability of MBSE tool to integrate with other corporate / legacy tools
Obstacle | Tooling | TQIS | Insufficient quality of tools and methods. Lots and lots of COTS tuning and tweaking resulting in a buggy tool chain. Experience with RSA, UML profiles to define DSLs, and oAW to access model. UML has a SW-origin that SysML does not hide.
Obstacle | Tooling | TQIS | Lack of tools and languages truly adapted to system engineering practices
Obstacle | Tooling | TQIS | Time-consuming diagram layouts and rendering
Obstacle | Tooling | TQIS | Poor modelling tool ergonomics / user experience
Obstacle | Tooling | TQIS | Having a tool not adapted for certain engineering domain: For example, not easy to use modeling method/tool for network systems (intanciation, reusing with another alias, meaning of functionnal exchanges, sdu/pdu...)
Obstacle | Tooling | TQIS | Users wishing they could have one single tool for everything
Enabler | Trend | MCW | Reaching a critical mass. If MBSE widespreads in organisations (industry, governments, etc.), it benefits in understanding, adoption becomes easier: If everybody does MBSE, you do MBSE!
Enabler | Trend | MCW | Risk of not doing MBSE!
Enabler | Trend | MCW | Industry impetus driving uptake of MBSE
Enabler | Trend | MCW | Customer pull: The customer dictates the use of MBSE
Obstacle | Trend | MCW | Having competing but related initiatives. One example is Enterprise Architecture with Architecture Frameworks: It is difficult to explain to non-engineers or decision-makers how it is related to MBSE, it is likely to create confusion.
Obstacle | Trend | MCW | Lack of alignment of university teaching / industry and government needs. There is a lot to learn (new processes, tools, etc.) and it is tough to find trainers who are available and adaptable.

## DO NOT EDIT
| Enabler | Obstacle
Coaching | 3 | 1
Commitment to MBSE | 6 | 8
Cultural Change | 2 | 12
Deployment Strategy | 7 | 0
Deployment Trick | 2 | 0
IT Policies and Tool Support | 2 | 5
Learning Curve | 0 | 3
MBSE Examples | 3 | 2
Modelling Guidelines | 2 | 3
Modelling Objectives | 1 | 2
Not MBSE-specific | 0 | 2
Other Stakeholders | 1 | 1
ROI Measurement | 1 | 3
Sponsorship | 1 | 2
Tooling | 3 | 11
Trend | 4 | 2
Expected Benefits | 7 | 0